JEC Compliance Hub Engineering Backlog & Implementation Roadmap FastAPI · SQLite → PostgreSQL · Static JS → React ¦ 4 Phases ¦ Stack-Accurate

| Field | Value | Notes |
| --- | --- | --- |
| Product | JEC Compliance Hub | Internal GRC platform |
| Current Stack | FastAPI + SQLite + Static JS | APScheduler, MSAL, python-multipart |
| Target Stack | FastAPI + PostgreSQL + React (componentised) | Next.js optional in later phase |
| Document | Engineering Backlog v1.0 | Aligned to PRD v1.0 + User Journey Guide v1.0 |
| Approach | Incremental evolution — not a rewrite | Backend preserved; domain model expanded first |
| Phases | 4 phases, each shippable independently | Phase 1 delivers auditor-usable product |

# 1. Implementation Strategy

The goal is not a rewrite. The FastAPI backend has working concepts for controls, evidence, dashboard, and integrations. The gap is domain model depth and workflow completeness — not the language or framework. The strategy is to evolve what exists into what the PRD requires, layer by layer.

| Principle | What It Means | Why |
| --- | --- | --- |
| Backend-first evolution | Expand schema and APIs before touching the frontend | Frontend cannot be operational if the backend does not support the workflows |
| SQLite now, Postgres later | Keep SQLite for Phase 1 and 2; migrate in Phase 2 end | Avoid migration complexity slowing down the first shippable milestone |
| Static JS → componentised React | Refactor the frontend incrementally, screen by screen | Avoids a big-bang frontend rewrite while workflow screens are still in flux |
| Phase 1 = auditor-usable | Phase 1 must produce a packet an auditor can actually evaluate | The PRD's explicit Phase 1 requirement — everything else is additive |
| Never break what works | Existing controls/evidence/dashboard routes stay functional | Continuity of current usage while new modules are added |

| Key decision | The existing app/db.py schema is the baseline. Every new table is additive — existing tables get ALTERed, not dropped. Alembic migrations manage all schema changes from Phase 1 onwards. |
| --- | --- |

## 1.1 What Already Works (Keep It)

| Existing Module | What To Preserve |
| --- | --- |
| Controls (app/main.py) | Routes and data model — add fields, do not replace |
| Evidence (upload flow) | File reference pattern to SharePoint stays; add workflow state on top |
| Dashboard (metrics) | Refactor to pull from real workflow counts once task engine exists |
| Integrations (MSAL/APScheduler) | Scheduler and auth plumbing stays; add run logging and evidence attachment |
| Auth / Workspaces | Extend RBAC model; do not replace the auth flow |
| Static frontend (frontend/) | Keep serving from FastAPI; refactor individual screens to React components progressively |

## 1.2 What Must Be Built (Missing or Too Thin)

| Missing Module | Gap Description |
| --- | --- |
| Evidence workflow states | Submitted → Approved → Rejected → Locked with SHA-256 hash and period linkage |
| Task engine | App-native tasks tied to controls, evidence, findings, policies — source of My Work |
| Audit lifecycle | Audit creation, workspace, in-scope controls, findings, packet export |
| Immutable audit log | append-only table: who changed what, when, previous state — no UPDATE/DELETE |
| Documents / policy versioning | Draft → Review → Published → Archived with diff and control linkage |
| Risk register | Risk records, scoring, treatment, action tracker, snapshots |
| Vendor review lifecycle | Vendor inventory, reviews, evidence requests, findings, closure |
| Notifications | Triggered in-app and email alerts per event type and persona |
| Trust center publishing | Customer-facing trust page from internal control data |
| Frontend component architecture | React-componentised screens replacing monolithic static JS |

# 2. Phase 1 — Audit-Ready Core (Weeks 1–5)

PHASE 1

Phase 1 exit condition: a Compliance Lead can run a complete SOC 2 Type 1 audit cycle — define controls, collect evidence through an approval workflow, generate a signed audit packet — without touching a spreadsheet or SharePoint folder manually.

## 2.1 Phase 1 Epic Summary

| ID | Epic | Pri | Effort | Personas | Description |
| --- | --- | --- | --- | --- | --- |
| E1.1 | Alembic + Schema Foundations | P0 | M | Backend | Install Alembic. Write migration baseline from current db.py. All future schema changes via migrations only. |
| E1.2 | Evidence Workflow Engine | P0 | L | Compliance Lead, IT Owner | Add status, audit_period, approver, locked_at, sha256_hash to evidence. Implement state machine: Submitted → Approved/Rejected → Locked. |
| E1.3 | Task Engine & My Work API | P0 | L | All personas | New tasks table. Task generation on evidence due, control gap, finding open. My Work API with filters. Notification hooks. |
| E1.4 | Immutable Audit Log | P0 | S | Admin, Auditor | append-only audit_log table. Log every mutation: actor, action, object_type, object_id, diff. No UPDATE/DELETE on this table ever. |
| E1.5 | Audit Lifecycle | P0 | XL | Compliance Lead, Auditor | audits + audit_controls + audit_findings tables. Audit creation, workspace, evidence queue, findings CRUD, period coverage view, packet export. |
| E1.6 | RBAC Hardening | P1 | M | Admin | Expand roles to: Admin, Compliance Manager, Security Reviewer, Contributor, Viewer. Enforce per-route and per-object. |
| E1.7 | Home Dashboard (Real Data) | P1 | S | All personas | Rebuild dashboard metrics from real workflow counts: controls passing, evidence stale, tasks open, audit countdown. |
| E1.8 | Audit Packet Export | P0 | M | Compliance Lead, Auditor | ZIP generation: control narratives, approved+locked evidence files with metadata, findings log CSV, manifest PDF. |

## 2.2 Phase 1 — Database Schema Changes

| Table | Action | Key Columns / Changes | Notes |
| --- | --- | --- | --- |
| alembic_version | CREATE | Standard Alembic tracking table | Required before any migrations run |
| evidence | ALTER | + status (enum: submitted/approved/rejected/locked), + audit_period_id (FK), + approver_id (FK), + approved_at, + rejected_reason, + locked_at, + sha256_hash, + collection_due_date, + period_start, + period_end | Core of Phase 1. Existing rows default to status=approved to preserve continuity. |
| audit_periods | CREATE | id, workspace_id, name, period_start, period_end, type (type1/type2), created_at | Links evidence to a defined observation window |
| audits | CREATE | id, workspace_id, period_id (FK), type, firm_name, status (enum), scope_notes, created_by, created_at, closed_at | One audit per period in v1 |
| audit_controls | CREATE | id, audit_id (FK), control_id (FK), evidence_status (enum), assigned_to (FK), notes | Join table — tracks per-control evidence state within an audit |
| audit_findings | CREATE | id, audit_id (FK), control_id (FK), title, description, severity (enum), status (enum), owner_id (FK), due_date, closed_at, remediation_notes | Findings are the audit output record |
| tasks | CREATE | id, workspace_id, type (enum), source_object_type, source_object_id, title, description, owner_id (FK), due_date, status (enum), priority (enum), created_at, completed_at | Single task table — source_object polymorphically links to any object |
| audit_log | CREATE | id, workspace_id, actor_id (FK), action, object_type, object_id, previous_state (JSON), new_state (JSON), created_at | append-only. Application layer enforces no UPDATE/DELETE. Index on object_type+object_id. |
| users | ALTER | + role (enum: admin/compliance_manager/security_reviewer/contributor/viewer), + is_active, + last_login | Expand from basic user model to RBAC-capable record |
| controls | ALTER | + owner_id (FK → users), + collection_schedule (enum: monthly/quarterly/annual/continuous), + tsc_criteria_ref, + test_procedure, + status (enum) | Add fields PRD requires. Existing controls get owner_id=NULL initially — admin assigns. |

## 2.3 Phase 1 — New & Extended API Endpoints

| Verb | Path | Role | Description | Status |
| --- | --- | --- | --- | --- |
| GET | /api/evidence | Contributor+ | List evidence with filters: status, control_id, period_id, owner_id, stale (bool) | EXTEND |
| POST | /api/evidence | Contributor+ | Submit evidence. Sets status=submitted. Triggers task notification to approver. | EXTEND |
| PATCH | /api/evidence/{id}/approve | ComplianceMgr+ | Approve evidence. Sets status=approved, approver_id, approved_at. Compute sha256 if file. Update control status. | NEW |
| PATCH | /api/evidence/{id}/reject | ComplianceMgr+ | Reject evidence. Sets status=rejected, rejected_reason. Re-notifies submitter. Reopens task. | NEW |
| PATCH | /api/evidence/{id}/lock | ComplianceMgr+ | Lock evidence to audit period. Computes SHA-256. Sets locked_at. Prevents further modification. | NEW |
| GET | /api/audit-periods | Contributor+ | List audit periods for workspace. | NEW |
| POST | /api/audit-periods | ComplianceMgr+ | Create audit period. Validates no overlap with existing periods. | NEW |
| GET | /api/audits | Contributor+ | List audits with status and completion % for each. | NEW |
| POST | /api/audits | ComplianceMgr+ | Create audit. Loads in-scope controls into audit_controls. Sets status=in_progress. | NEW |
| GET | /api/audits/{id}/workspace | Contributor+ | Full audit workspace: controls, evidence status per control, findings, owner assignments, completion %. | NEW |
| GET | /api/audits/{id}/coverage | Contributor+ | Period coverage view: evidence items on a timeline, gap months highlighted. Essential for Type 2. | NEW |
| POST | /api/audits/{id}/findings | SecurityReviewer+ | Create finding. Links to audit + control. Sets severity, owner, due_date. | NEW |
| PATCH | /api/audits/{id}/findings/{fid} | SecurityReviewer+ | Update finding: status, remediation notes, close date. | NEW |
| GET | /api/audits/{id}/export | ComplianceMgr+ | Generate and stream audit packet ZIP: manifest, narratives, evidence files, findings CSV. | NEW |
| GET | /api/tasks | Contributor+ | List tasks. Filters: owner_id, status, type, due_before. Sorted by due_date ASC. | NEW |
| POST | /api/tasks | ComplianceMgr+ | Create task manually. System also creates tasks automatically on trigger events. | NEW |
| PATCH | /api/tasks/{id} | Contributor+ | Update task: status, completion notes. Owner can only update their own tasks. | NEW |
| GET | /api/audit-log | Admin | Query immutable audit log. Filters: actor_id, object_type, object_id, date range. | NEW |
| GET | /api/dashboard | Contributor+ | Rebuilt: real counts from tasks, evidence status, audit progress, findings. Not mock data. | EXTEND |
| GET | /api/controls/{id} | Contributor+ | Control detail: statement, criteria, owner, evidence timeline, open tasks, linked findings. | EXTEND |

## 2.4 Phase 1 — Key User Stories

| ID | User Story | Acceptance Criteria |
| --- | --- | --- |
| S1.1 | As a Compliance Lead, I want to submit and approve evidence items so that I can maintain a documented chain of custody for each control. | - Evidence can be submitted with: file or URL, period start/end, description, control linkage - Submitted evidence enters "Submitted" status and triggers an in-app notification to the approver - Approver can approve (→ Approved) or reject with a comment (→ Rejected) - Rejected evidence re-notifies the submitter with the rejection reason - Approved evidence can be locked to an audit period — locked items cannot be modified - Locking computes and stores SHA-256 hash of the file reference |
| S1.2 | As an IT Owner, I want My Work to show me exactly what evidence I need to submit and by when, so I don't need to understand the compliance framework to contribute. | - My Work lists all tasks assigned to me, sorted by due date - Each task row shows: what is needed, which control it supports, due date, instructions link - Clicking a task opens the evidence slot with pre-filled control and period - "What good looks like" guidance is visible on every evidence slot - Task status updates automatically when evidence is submitted/approved/rejected |
| S1.3 | As a Compliance Lead, I want to create an audit and see which evidence is missing so I can close gaps before the audit window. | - Audit creation requires: type (T1/T2), firm name, period reference, scope notes - Audit workspace loads all in-scope controls with their evidence status - Evidence completion % shown as a progress bar - Filtering to "Missing Evidence" controls shows only those without approved evidence in period - Bulk task assignment for missing controls: assigns to control owners with a shared due date |
| S1.4 | As a Compliance Lead, I want to generate an audit packet in one action so that I never manually assemble a ZIP of evidence files again. | - Export action generates a ZIP containing: manifest.txt, control_narratives/ folder, evidence/ folder, findings.csv - Manifest lists every included file with: control ref, period, uploaded by, approved by, SHA-256 hash, locked timestamp - Only Approved or Locked evidence items are included — never Submitted or Rejected - ZIP generation completes in under 60 seconds for up to 200 evidence items - Download is logged in audit_log with actor and timestamp |
| S1.5 | As an Admin, I want every data mutation to be logged immutably so that I can answer "who changed what and when" at any time. | - Every POST/PUT/PATCH/DELETE on a business object writes a row to audit_log - audit_log has no UPDATE or DELETE route — enforced at the application layer - Each log row contains: actor_id, action, object_type, object_id, previous_state (JSON), new_state (JSON), timestamp - GET /api/audit-log supports filters by actor, object_type, object_id, and date range - Audit log entries are included in the audit packet export |

## 2.5 Phase 1 — Frontend Changes (Static JS)

In Phase 1, the frontend stays as static JS served by FastAPI. The work is screen-level rewrites and new screens — not a framework migration.

| Screen | Changes Required |
| --- | --- |
| Home / Dashboard | Rebuild metric cards from real API: controls passing %, evidence stale count, open tasks, audit countdown. Every card clickable. |
| My Work (NEW) | New page. Task list table with filters (mine / overdue / by type). Each row links to source object. Status chip updates inline. |
| Evidence List | Add status filter chips (Submitted / Approved / Rejected / Locked / Stale). Add period selector. Show approver column. |
| Evidence Slot (NEW) | New view per evidence item: shows control, period, guidance, upload/link, approval history, rejection comment if applicable. |
| Control Detail | Add: evidence timeline, open tasks list, linked findings, action bar (Add Evidence / Create Task / Link Policy). |
| Audits (NEW) | Audit list, audit creation form, audit workspace (controls + evidence + findings tabs), packet export button. |
| Audit Log (NEW) | Read-only table. Filter by actor, object type, date. Admin only. CSV export. |

| Constraint | All Phase 1 frontend work stays in the existing static JS pattern. Do not start the React migration during Phase 1 — it adds risk with no direct Phase 1 benefit. React migration starts in Phase 2 after workflows are stable. |
| --- | --- |

# 3. Phase 2 — Policies, Notifications & PostgreSQL (Weeks 6–10)

PHASE 2

Phase 2 completes the operational compliance loop: policies get a lifecycle, notifications make the platform self-driving, the dashboard becomes the real posture read, and the database migrates to PostgreSQL. The React frontend migration begins here.

## 3.1 Phase 2 Epic Summary

| ID | Epic | Pri | Effort | Personas | Description |
| --- | --- | --- | --- | --- | --- |
| E2.1 | Documents & Policy Versioning | P0 | L | Compliance Lead, Employee | documents + document_versions tables. Draft→Review→Published→Archived lifecycle. Control linkage. Review due dates. Acknowledgement tracking. |
| E2.2 | Notification System | P0 | L | All personas | notifications table + APScheduler jobs for stale evidence, due dates, overdue tasks, integration failures. In-app + email delivery. |
| E2.3 | Home Dashboard Rebuild | P1 | M | All personas | Replace mock/static metrics with real aggregated counts from tasks, evidence status, audit progress. Add trend arrows and drill-down links. |
| E2.4 | PostgreSQL Migration | P1 | M | Backend / Ops | Alembic migration to PostgreSQL. Update connection string + db.py. Validate all existing queries. Keep SQLite for local dev via env flag. |
| E2.5 | React Frontend — Core Screens | P1 | XL | All personas | Componentise Home, My Work, Controls, Evidence screens into React. Serve via FastAPI static mount initially. No Next.js yet. |
| E2.6 | Type 2 Period Coverage View | P1 | M | Compliance Lead, Auditor | Timeline visualisation of evidence coverage across the full observation period. Highlights gap months. Linked to audit workspace. |
| E2.7 | RBAC — Object-Level Enforcement | P1 | M | Admin | Per-object permission checks on evidence, audit, findings, policies. Role middleware refactored into reusable dependency. |

## 3.2 Phase 2 — Database Schema Changes

| Table | Action | Key Columns / Changes | Notes |
| --- | --- | --- | --- |
| documents | CREATE | id, workspace_id, title, type (policy/procedure/standard), owner_id (FK), current_version_id (FK nullable), review_due_date, created_at | One record per document regardless of versions |
| document_versions | CREATE | id, document_id (FK), version_num, status (enum: draft/review/published/archived), file_ref, published_by (FK), published_at, archived_at, change_summary | Version chain. Only one version per document has status=published at a time. |
| document_controls | CREATE | document_id (FK), control_id (FK), PRIMARY KEY (document_id, control_id) | Many-to-many: a policy can support multiple controls |
| acknowledgements | CREATE | id, document_version_id (FK), user_id (FK), acknowledged_at | Tracks policy acknowledgement per user per version |
| notifications | CREATE | id, workspace_id, recipient_id (FK), type (enum), object_type, object_id, message, read_at, created_at | In-app notifications. Email delivery uses separate job referencing this table. |
| notification_prefs | CREATE | user_id (FK), notification_type (enum), email_enabled (bool), inapp_enabled (bool) | Per-user notification preferences |
| controls | ALTER | + review_due_date, + last_test_result (enum), + last_tested_at | Supports test result display on control detail |

## 3.3 Phase 2 — New API Endpoints

| Verb | Path | Role | Description | Status |
| --- | --- | --- | --- | --- |
| GET | /api/documents | Viewer+ | List documents with version status, review due date, owner. | NEW |
| POST | /api/documents | ComplianceMgr+ | Create document record and first draft version. | NEW |
| GET | /api/documents/{id}/versions | Viewer+ | List all versions for a document with status and timestamps. | NEW |
| POST | /api/documents/{id}/versions | ComplianceMgr+ | Create new draft version. Locks previous published version to archived. | NEW |
| PATCH | /api/documents/{id}/versions/{vid}/publish | ComplianceMgr+ | Publish version. Archives previous published version. Triggers acknowledgement tasks if required. | NEW |
| POST | /api/documents/{id}/versions/{vid}/acknowledge | Contributor+ | Record user acknowledgement. Closes related acknowledgement task. | NEW |
| GET | /api/notifications | Contributor+ | List notifications for current user. Filter: unread, type, date. | NEW |
| PATCH | /api/notifications/{id}/read | Contributor+ | Mark notification as read. | NEW |
| GET | /api/audits/{id}/coverage | Contributor+ | Period coverage data: evidence timestamps mapped against observation window months. Returns gap array. | NEW |
| GET | /api/reports/readiness | ComplianceMgr+ | Audit readiness report: control health, evidence freshness, open gaps, findings summary. Returns JSON + PDF stream. | NEW |

## 3.4 Phase 2 — APScheduler Jobs

| Job | Schedule | Description |
| --- | --- | --- |
| evidence_staleness_check | Daily 08:00 | Marks evidence as stale if past collection_due_date. Creates overdue task if not already exists. Notifies owner. |
| task_due_reminder | Daily 08:00 | Sends reminder for tasks due in 7 days. Escalates to Compliance Lead if task is overdue >48 hours. |
| policy_review_reminder | Weekly Monday | Checks documents where review_due_date < now + 30 days. Creates review task if none exists. Notifies owner. |
| integration_health_check | Every 30 min | Checks last_run for each integration connector. Sets status=error if no successful run in expected window. Notifies Admin. |
| audit_countdown_alert | Weekly Monday | For audits within 30 days, sends readiness summary to Compliance Lead: completion %, missing evidence count. |
| monthly_posture_snapshot | 1st of month | Records current posture metrics (% passing, stale count, open findings) as a dated snapshot for trend charts. |

## 3.5 Phase 2 — React Migration Plan

Migrate screen by screen. FastAPI continues serving the static mount. No Next.js yet — that is an optional Phase 4 consideration.

| Screen | Order | Migration Notes |
| --- | --- | --- |
| My Work | 1st | Highest daily-use screen. Clean React component with task table, filters, status chips. Replaces Phase 1 static build. |
| Home Dashboard | 2nd | React component with metric cards and drill-down links. Pulls from rebuilt /api/dashboard. |
| Evidence List + Slot | 3rd | React with approval workflow UI, period selector, file upload, rejection comment display. |
| Control Detail | 4th | React slide-over or full page with evidence timeline, task list, findings, policy links. |
| Audit Workspace | 5th | Most complex Phase 1 screen. React tabs: Evidence Queue, Findings, Assignments, Coverage view. |
| Documents / Policies | 6th | React with version list, publish/archive actions, diff view between versions, acknowledgement status. |

# 4. Phase 3 — Risk, Vendors & Trust Center (Weeks 11–16)

PHASE 3

Phase 3 adds the two largest remaining workflow modules (Risk and Vendors) and turns the internal compliance posture into customer-facing trust assets. The React frontend is now the primary interface for all new screens.

## 4.1 Phase 3 Epic Summary

| ID | Epic | Pri | Effort | Personas | Description |
| --- | --- | --- | --- | --- | --- |
| E3.1 | Risk Register | P0 | L | Security Lead | risks + risk_actions + risk_snapshots tables. CRUD, likelihood/impact scoring, treatment workflow, action tracker, monthly snapshot, trend chart. |
| E3.2 | Vendor Review Lifecycle | P0 | XL | Vendor Reviewer | vendors + vendor_reviews + vendor_review_evidence + vendor_findings tables. Full review lifecycle from inventory to closure with findings and residual risk rating. |
| E3.3 | Trust Center Publishing | P1 | L | Compliance Lead, Customer | trust_controls + trust_articles tables. Admin selects visible controls/policies. Generates public trust page served at /trust. Download tracking. |
| E3.4 | Reports Module | P1 | M | Executive, Compliance Lead | Pre-built report types: Audit Readiness, Trust Posture, Vendor Summary, Risk Summary, Activity Log. JSON + PDF export. Scheduled email delivery option. |
| E3.5 | Knowledge Base (Trust FAQs) | P2 | S | Compliance Lead, Customer | trust_kb_articles table. Reusable answers to common security questionnaire questions. Surfaced on trust center. Compliance Lead manages content. |
| E3.6 | Assets & Personnel Stubs | P2 | M | Security Lead, Admin | Lightweight asset inventory and personnel record tables. Stubs for Phase 4 integration feeds. Not full MDM — just structured records for evidence linkage. |

## 4.2 Phase 3 — Database Schema Changes

| Table | Action | Key Columns / Changes | Notes |
| --- | --- | --- | --- |
| risks | CREATE | id, workspace_id, category, title, description, likelihood (1-5), impact (1-5), inherent_score (computed), treatment (enum), residual_score, owner_id (FK), status, review_date, created_at | Core risk record. inherent_score = likelihood * impact, stored as computed field. |
| risk_actions | CREATE | id, risk_id (FK), title, description, owner_id (FK), due_date, status, completed_at | Remediation/treatment actions linked to a risk |
| risk_snapshots | CREATE | id, workspace_id, snapshot_date, high_count, medium_count, low_count, total_score, raw_data (JSON) | Monthly snapshot for trend chart. Written by APScheduler job. |
| risk_library | CREATE | id, category, title, description, default_likelihood, default_impact, tags | Pre-built risk templates. Workspace-specific risks instantiate from library. |
| vendors | CREATE | id, workspace_id, name, category, tier (enum: critical/high/medium/low), primary_contact, data_types_processed, inherent_risk, review_status, last_review_id (FK nullable), created_at | Vendor inventory record |
| vendor_reviews | CREATE | id, vendor_id (FK), reviewer_id (FK), status (enum), start_date, close_date, overall_risk_rating, summary_notes, next_review_due | One active review per vendor at a time. Closed reviews are historical. |
| vendor_review_evidence | CREATE | id, review_id (FK), item_title, description, status (enum: requested/received/accepted/not_applicable), file_ref, uploaded_by (FK), uploaded_at, notes | Evidence request items within a vendor review |
| vendor_findings | CREATE | id, review_id (FK), vendor_id (FK), title, description, severity (enum), status (enum), owner_id (FK), due_date, closed_at, compensating_controls | Findings from a vendor review — feed into risk register if high severity |
| trust_controls | CREATE | id, workspace_id, control_id (FK nullable), category, title, description, status, last_evidence_date, is_published, sort_order | Customer-safe control representations. Not the internal control record. |
| trust_artifacts | CREATE | id, workspace_id, title, type, file_ref, is_public, download_count, published_at, expires_at | Downloadable artifacts on trust center: SOC 2 reports, policies, certs |
| trust_kb_articles | CREATE | id, workspace_id, question, answer, category, is_published, sort_order, created_by (FK), updated_at | Knowledge base entries for trust center FAQ section |
| trust_access_log | CREATE | id, workspace_id, visitor_email (nullable), artifact_id (FK nullable), action, ip_hash, created_at | Logs trust center downloads and page visits. No PII beyond email if provided. |

## 4.3 Phase 3 — Key API Endpoints

| Verb | Path | Role | Description | Status |
| --- | --- | --- | --- | --- |
| GET | /api/risks | Viewer+ | List risks with filters: severity, treatment, owner, status, review_due. | NEW |
| POST | /api/risks | SecurityReview+ | Create risk. Can instantiate from risk_library template. | NEW |
| PATCH | /api/risks/{id} | SecurityReview+ | Update risk: scores, treatment, review date. | NEW |
| GET | /api/risks/snapshots | Viewer+ | Risk posture trend data. Returns array of dated snapshots for chart rendering. | NEW |
| GET | /api/vendors | Viewer+ | Vendor inventory list with tier, review status, overdue badge. | NEW |
| POST | /api/vendors | SecurityReview+ | Add vendor to inventory. | NEW |
| POST | /api/vendors/{id}/reviews | SecurityReview+ | Start new vendor review. Checks no active review exists for this vendor. | NEW |
| GET | /api/vendors/{id}/reviews/{rid} | SecurityReview+ | Vendor review workspace: evidence items, findings, status, summary. | NEW |
| PATCH | /api/vendors/{id}/reviews/{rid}/close | SecurityReview+ | Close vendor review. Sets overall risk rating. Updates vendor.review_status. Sets next_review_due. | NEW |
| POST | /api/vendors/{id}/reviews/{rid}/findings | SecurityReview+ | Log finding against a vendor review. | NEW |
| GET | /trust | Public | Public trust center page. Served from /trust route. No auth required for public tier. | NEW |
| GET | /api/trust/controls | Public | Published trust controls by category. | NEW |
| GET | /api/trust/artifacts/{id}/download | Public | Download trust artifact. Logs access to trust_access_log. | NEW |
| GET | /api/reports/{type} | ComplianceMgr+ | Generate report. Types: readiness, trust_posture, vendor_summary, risk_summary. Returns JSON or PDF stream. | NEW |

# 5. Phase 4 — Automation, AI & External Access (Weeks 17+)

PHASE 4

Phase 4 makes the platform self-driving: connectors pull evidence automatically, drift is detected and surfaced, and the AI agent turns passive data into active suggestions. External auditor and customer flows also land here.

## 5.1 Phase 4 Epic Summary

| ID | Epic | Pri | Effort | Personas | Description |
| --- | --- | --- | --- | --- | --- |
| E4.1 | Scheduled Evidence Connectors | P0 | XL | Compliance Lead, Admin | API connectors for Azure AD, GitHub, AWS IAM, Jira. Each connector pulls evidence, snapshots result, attaches to mapped controls, logs run. |
| E4.2 | Drift Detection & Tests | P0 | L | Security Lead | tests table. Continuous test execution from connector data. Drift alerts: MFA disabled, branch protection changed, IAM key rotation missed. |
| E4.3 | JEC Agent (AI Suggestions) | P1 | L | Compliance Lead, Security | Anthropic API integration. Agent suggests: close evidence gaps, remediate findings, draft policy language, summarise audit posture. All suggestions link to source objects. |
| E4.4 | External Auditor Portal (v2) | P1 | L | Auditor | Scoped read-only access for external auditors. Token-based login. See only in-scope audit controls and locked evidence. Comment threads on controls. |
| E4.5 | Next.js Migration (Optional) | P3 | XL | Frontend / Backend | Migrate React frontend to Next.js App Router. API routes replace FastAPI for frontend-facing endpoints. FastAPI retained for heavy backend jobs and connectors. |
| E4.6 | Multi-Workspace / Multi-Entity | P2 | L | Admin | Full workspace isolation for multiple JEC entities or environments. Shared framework library across workspaces. Per-workspace RBAC. |

## 5.2 Phase 4 — Connector Architecture

Each connector follows the same pattern. New connectors can be added without touching core application code.

| Connector | Phase B/C | Evidence Produced | Controls Mapped |
| --- | --- | --- | --- |
| Azure AD | Phase B | User list, group memberships, MFA status per user | CC6.1 (Logical Access), CC6.2 (Authentication), CC6.3 (Access Removal) |
| GitHub | Phase B | Branch protection rules export, audit log events | CC8.1 (Change Management), CC7.2 (System Monitoring) |
| AWS | Phase B | IAM credential report, CloudTrail enabled status, Config rules | CC6.6 (Logical Access Restrictions), CC7.1 (Infrastructure Monitoring) |
| Jira | Phase B | Change request tickets, incident tickets | CC7.4 (Incident Response), CC8.1 (Change Management) |
| HRIS | Phase C | Onboarding/offboarding records, role changes | CC6.1 (Personnel Access), CC6.3 (Termination Process) |
| Endpoint/MDM | Phase C | Device compliance report, encryption status | CC6.8 (Device Management) |

## 5.3 Connector Data Model (Additional Tables)

| Table | Action | Key Columns / Changes | Notes |
| --- | --- | --- | --- |
| integration_connectors | CREATE | id, workspace_id, type (enum), name, credentials_ref (encrypted), status, last_run_at, last_run_status, next_run_at, run_interval_hours | One row per configured integration |
| integration_runs | CREATE | id, connector_id (FK), started_at, completed_at, status, items_collected, items_failed, error_message, raw_result_ref | Run history for each connector. Keeps last 90 runs per connector. |
| tests | CREATE | id, workspace_id, control_id (FK), name, method (enum: automated/manual), connector_id (FK nullable), last_run_at, last_result (enum), failure_reason, evidence_snapshot_id (FK nullable) | Test records derived from connector data. Automated tests re-run on each connector pull. |
| agent_suggestions | CREATE | id, workspace_id, type (enum), source_object_type, source_object_id, suggestion_text, suggested_action, status (enum: pending/accepted/dismissed), created_at, acted_on_at | AI agent output. Always linked to a source object. |

# 6. Dependencies & Build Sequencing

Some epics have hard dependencies. Build these in the wrong order and you will write code twice.

| Epic | Depends On | Blocks | Reason |
| --- | --- | --- | --- |
| E1.1 | — | Everything | Alembic must exist before any schema change. First thing to do. |
| E1.4 | E1.1 | E1.5, E2.7 | Audit log must exist before audit lifecycle writes to it. RBAC depends on log. |
| E1.2 | E1.1 | E1.3, E1.5, E1.8 | Evidence workflow is the core of Phase 1. Tasks and audits both depend on evidence state. |
| E1.3 | E1.2 | E2.2, E3.x | Task engine depends on evidence state machine. Notifications depend on tasks. |
| E1.5 | E1.2, E1.4 | E1.8, E2.6 | Audit lifecycle needs evidence states and audit log. Export and coverage view need the audit. |
| E2.1 | E1.3 | E3.3 | Documents need task engine for review tasks. Trust center publishing needs published documents. |
| E2.2 | E1.3, E2.1 | E4.1, E4.3 | Notifications need tasks. Connector alerts and agent suggestions both use the notification system. |
| E2.4 | E1.x done | E3.x, E4.x | PostgreSQL migration should happen after Phase 1 is stable and before Phase 3 adds schema volume. |
| E3.2 | E1.3, E3.1 | E4.1 | Vendor reviews depend on task engine and risk register (findings feed risks). Connectors monitor vendors. |
| E4.2 | E4.1 | E4.3 | Drift detection depends on connector data. AI agent suggestions depend on test results and drift signals. |

# 7. Technical Decisions & Constraints

| Decision | Choice | Rationale |
| --- | --- | --- |
| Migration tool | Alembic (autogenerate off; manual migrations only) | Autogenerate produces unsafe migrations. Manual migrations are explicit and reviewable. |
| Evidence hashing | SHA-256 of file bytes at lock time | Industry standard. Computed and stored once on lock. Re-verified on every read during an active audit. |
| Audit log enforcement | Application-layer: no DELETE/UPDATE route on audit_log | DB-level row security in Postgres (Phase 2+). App layer enforces in Phase 1 with SQLite. |
| Credential storage | Encrypted at rest via Fernet key in env. Never in DB plaintext. | Integration connector tokens and secrets. Key rotation procedure documented. |
| File storage | SharePoint references in Phase 1+2. S3-compatible optional in Phase 3. | SharePoint already exists and MSAL auth is in the repo. Avoids double storage. |
| React bundling (Phase 2) | Vite + React. Served as static mount from FastAPI. | No Node.js server required. FastAPI handles all API requests. Simplest migration path. |
| AI integration (Phase 4) | Anthropic API (claude-sonnet-4-20250514) via httpx | Direct API calls from FastAPI. No SDK required. Streaming supported via SSE endpoint. |
| Email notifications | SMTP via Python smtplib or SendGrid. APScheduler job dispatches. | No new dependency for smtplib. SendGrid optional for production reliability. |
| Test strategy | pytest for backend. Vitest for React components. | pytest already viable with FastAPI. Vitest is the natural Vite companion. |
| SQLite → Postgres timing | End of Phase 2 (after Phase 1 stable) | Migrate after all Phase 1 tables are confirmed correct. Alembic handles the switch via env var. |

# 8. Definition of Done — Per Phase

| Phase | Exit Criteria |
| --- | --- |
| 1 | - Alembic baseline migration exists and all new tables created via migration only - Evidence has a working state machine: Submitted → Approved → Rejected → Locked with SHA-256 hash stored on lock - My Work page shows real tasks with correct filtering by owner, status, and type - Audit can be created, workspace shows evidence completion %, findings can be logged and tracked - Audit packet export generates a valid ZIP with manifest, control narratives, evidence files, findings CSV - audit_log records every mutation with actor, timestamp, and diff — no DELETE or UPDATE route exists - Role-based access enforced: Contributor cannot approve evidence; Viewer cannot create tasks |
| 2 | - Policy versioning: Draft → Published → Archived works with only one Published version at a time - APScheduler jobs run on schedule: staleness check, task reminders, policy review alerts, integration health - In-app notifications appear for all trigger events defined in the notification matrix - PostgreSQL migration complete: all Phase 1 data migrated, all existing tests pass against Postgres - At least My Work, Home, and Evidence screens are React-componentised and deployed from Vite build - Type 2 period coverage view shows evidence dates on timeline with gap months highlighted |
| 3 | - Risk register: create, score, treat, assign action, snapshot. Monthly snapshot job runs. - Vendor review: full lifecycle from inventory to closed review with findings and residual risk rating - Trust center: Compliance Lead can publish selected controls and artifacts to /trust public page - At least 3 report types generate correctly: Audit Readiness, Trust Posture, Risk Summary - All Phase 3 screens are React-componentised — no remaining static JS for new screens |
| 4 | - At least 2 automated connectors pulling evidence on schedule and attaching to controls (Azure AD + GitHub minimum) - Drift detection: failing tests surface in Home and Security Lead's My Work within 1 hour of connector run - JEC Agent returns suggestions with links to source objects. Suggestions are dismissible or actioned. - External auditor can log in with scoped token, view locked evidence, and post comment threads on controls |

# 9. Engineering Risks & Mitigations

| Risk | Severity | Scenario | Mitigation |
| --- | --- | --- | --- |
| SHA-256 hash computed on URL reference, not file bytes | High | SharePoint file could change after lock without detection | Hash the downloaded file bytes at lock time. Store both URL and hash. Re-verify on download during audit. |
| SQLite concurrency under multi-user load | Medium | Write contention during audit prep when many contributors submit evidence simultaneously | SQLite WAL mode in Phase 1. PostgreSQL migration in Phase 2 removes this entirely. |
| MSAL token expiry breaking scheduled connectors | Medium | Azure AD integration silently stops pulling evidence | Integration health check job every 30 min. Error state surfaced on Home. Admin email alert on failure. |
| audit_log grows unbounded | Low | Table becomes unqueryable after 12+ months of high activity | Partition by month in PostgreSQL. Archive logs older than retention policy to cold storage. Index on created_at. |
| React migration disrupts existing users mid-phase | Medium | Partial React rollout leaves users on inconsistent UI | Screen-by-screen migration. Old static JS screens remain live until React replacement is confirmed stable. Feature flag per screen. |
| AI agent suggestions without source citations | Medium | Users act on agent output that cannot be traced to evidence | Every agent_suggestion row must have source_object_type + source_object_id set. Agent prompt enforces citation. Suggestions without source_object are rejected at API layer. |

| Remember | The fastest path to audit-ready is Phase 1 and only Phase 1. Do not let Phase 3 or Phase 4 scope creep into the first delivery. An auditor does not need the AI agent — they need approved evidence with a chain of custody. |
| --- | --- |